## MVP2 Execution Board
Task ID | Milestone | Task | Objective | Dependencies | Priority | Status | Architecture Gate | Implementation PR | Evidence / ADR | TD Closed / Addressed | Release Blocking | Acceptance Result | Guardrail / Notes
M2-T01 | M2-A | Architecture, contracts and ADR freeze | Freeze MVP-2 ownership, boundaries, contracts and ADRs | — | P0 | Not Started | BLOCKED |  |  | No | No |  | T01 must pass before implementation
M2-T02 | M2-A | Transactional outbox | Make AI work durable and address TD-T18-01 | T01 | P0 | Not Started | BLOCKED |  |  | TD-T18-01 | Yes |  | Authoritative change + outbox in one transaction
M2-T03 | M2-A | Durable dispatcher / idempotency | Retries, leases, replay and exactly-once business effect | T02 | P0 | Not Started | BLOCKED |  |  | TD-T18-01 | Yes |  | No lost work; duplicates harmless
M2-T04 | M2-A | AI provenance v2 | Persist provider/model/route version and immutable execution provenance | T01,T02 | P0 | Not Started | BLOCKED |  |  | TD-RC8-02 | Yes |  | Must complete before Diagnostic Agent
M2-T05 | M2-B | Grounded Context Contract | Versioned bounded context package for agents | T04 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Facts separated from model summaries
M2-T06 | M2-B | Evidence/context retrieval | Deterministic authorized retrieval of learner and curriculum context | T05 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Stable IDs and deterministic ordering
M2-T07 | M2-B | Grounding/evidence validation | Reject unsupported or fabricated evidence references | T05,T06 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Fail closed
M2-T08 | M2-C | Diagnostic Agent | Proposal-only diagnostic analysis | T02,T03,T04,T07 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | HARD GATE: T02-T04 accepted first
M2-T09 | M2-C | DiagnosticProposalGate | Deterministic validation/acceptance boundary | T08 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Agent never becomes authority
M2-T10 | M2-C | Diagnostic E2E evaluation | Golden scenarios, perturbation, failure paths | T09 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Behavior not wording
M2-T11 | M2-D | Assessment Evaluation Agent | Rubric-bound AI evaluation for non-deterministic responses | T04,T07,T10 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | Deterministic scoring remains first choice
M2-T12 | M2-D | EvaluationProposalGate | Validate evaluation before authoritative updates | T11 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | No unilateral AI final score
M2-T13 | M2-D | Learner feedback API/UI | Expose approved feedback safely | T12 | P1 | Not Started | BLOCKED |  |  | No | No |  | No raw prompts/hidden reasoning
M2-T14 | M2-E | Controlled multi-agent orchestration | Explicit evaluation→diagnosis→adaptation workflow | T10,T12 | P0 | Not Started | BLOCKED |  |  | No | Yes |  | No unbounded agent-to-agent loops
M2-T15 | M2-E | Reliability/performance/security qualification | Crash, retry, perturbation, security and performance gates | T13,T14 | P0 | Not Started | BLOCKED |  |  | TD-R1-03;TD-RC8-01 | Yes |  | Full-stack qualification
M2-T16 | M2-E | MVP-2 release qualification / closure | Immutable candidate evidence and release decision | T15 | P0 | Not Started | BLOCKED |  |  | All remaining | Yes |  | No historical evidence rewriting

## Dashboard
RAMALS MVP-2 Design / Execution Board
Metric | Value | Milestone | Purpose | Tasks | Entry | Exit
Total tasks | 16 | M2-A | Reliability & contracts | T01-T04 | MVP-1 closed | Durability + provenance accepted
P0 tasks | 15 | M2-B | Grounding | T05-T07 | M2-A PASS | Validated grounded context
MVP-1 debts carried | 4 | M2-C | Diagnosis | T08-T10 | M2-B PASS | Diagnostic E2E accepted
Hard foundation gate | T02 + T03 + T04 | M2-D | Evaluation | T11-T13 | Diagnosis foundation | Approved learner feedback
Diagnostic Agent start rule | T08 blocked until T02/T03/T04 accepted | M2-E | Orchestration & release | T14-T16 | Prior gates PASS | MVP-2 closure decision
Execution order: Reliability → Provenance → Grounding → Diagnostic → Assessment Evaluation → Learner Experience → Orchestration → Qualification
Governing invariant: Agents recommend. Deterministic services decide.
Recommended first action: Start M2-T01 only. Freeze contracts and ADRs, review them, then authorize T02.

## Lists
Status | Priority | Gate | Acceptance | Release Blocking
Not Started | P0 | BLOCKED |  | Yes
In Progress | P1 | READY | PASS | No
Blocked | P2 | PASS | FAIL
Accepted |  | FAIL | PASS_WITH_DEBT
Closed